## README
Remat Al-Riyadh — Data & Analytics KPI Tracker
Production-Grade · Cross-Sheet Dynamic · Dropdown-Driven
Owner: Saad ¦ Reports: Yasir (Data Engineering) · Ahmad (BI)
DATA FLOW (how the workbook is wired)
Lookups → source of all dropdown lists (Tiers, Statuses, Owners, Domains, etc.)
SLA Tiers → KPI × P1/P2/P3 target matrix (single source of truth for Operations targets)
Dashboard Portfolio → master register: tier, owners, stakeholders, governance rules
Ops SLA Tracker → pulls Name/Status/Tier from Portfolio; pulls Targets from SLA Tiers; only Actuals are inputs
Delivery Tracker → 7-stage milestone tracker; computed Delivery KPI Summary at bottom
Scorecard → pulls Operations actuals from Ops SLA Tracker; pulls Delivery actuals from Delivery Tracker
WHAT'S DYNAMIC (and what's input)
INPUTS (yellow cells):
· Dashboard Portfolio: Names, Tiers, Stakeholders, Governance rules (per dashboard)
· Ops SLA Tracker: Monthly Actuals per dashboard per KPI
· Delivery Tracker: Planned & Actual milestone dates
· Scorecard: Manual KPI actuals (Estimation accuracy, Defect escape rate, Fusion coverage, Pre-prod DQ)
AUTO-CALCULATED (locked cells):
· Tier per dashboard in Ops SLA Tracker → pulled from Portfolio
· SLA Targets per dashboard → HLOOKUP from SLA Tiers based on Tier
· RAG status everywhere → formula-driven (Green ≥100%, Amber 90–99%, Red <90%)
· Status & % Complete in Delivery Tracker → derived from milestone dates
· Delivery KPI Summary → SUMPRODUCT over the 15 dashboards
· Scorecard Operations actuals → AVERAGEIFS / SUMIFS from Ops SLA Tracker (Live only)
· Scorecard Delivery actuals → pulled from Delivery Tracker summary
· Overall role scores → weighted: 60% Ops + 30% own Delivery + 10% Joint Delivery
HOW TO USE
FIRST-TIME SETUP:
1. Dashboard Portfolio: fill in the 16 existing dashboards (Name, Domain, Tier, Source, Frequency, Stakeholders).
2. Validate the SLA Tiers targets reflect your actual organizational SLAs (P1 / P2 / P3 columns).
3. Adjust governance defaults (Access Rule, Change Control Rule) per dashboard if needed.
EVERY MONTH:
1. Update Period in Ops SLA Tracker (cell C4).
2. Enter Actual SLA values for each Live dashboard in Ops SLA Tracker.
3. Update Actual milestone dates in Delivery Tracker as stages complete.
4. Enter manual Scorecard actuals (Estimation accuracy, Defect escape, etc.) — only 4 cells.
5. Open the Scorecard — everything else has auto-calculated.
DROPDOWN LISTS (drive consistency)
Dashboard Portfolio: Domain · Status · Tier · DE Owner · BI Owner · Source · Frequency · Sensitivity
All lists live in the Lookups sheet — append new options there to extend.

## Scorecard
MONTHLY KPI SCORECARD
Auto-aggregated from Ops SLA Tracker and Delivery Tracker. Targets pull from SLA Tiers (P2 baseline).
Reporting Period: | MMM-YYYY
# | KPI | Owner | Direction | Target | Weight | Actual | Score | RAG | Source
PILLAR 1 — OPERATIONS (16 live dashboards · pulled from Ops SLA Tracker)
Operations · Data Engineering (Yasir)
1 | Pipeline availability | Yasir | H | 99.5% | 25% |  |  |  | Ops SLA Tracker (Avg, Live)
2 | Data freshness % met | Yasir | H | 95% | 25% |  |  |  | Ops SLA Tracker (Avg, Live)
3 | Pipeline failures / month | Yasir | L | 2 | 15% | 0 |  |  | Ops SLA Tracker (Sum, Live)
4 | Incident MTTR (hours) | Yasir | L | 4 | 15% |  |  |  | Ops SLA Tracker (Avg, Live)
5 | Data quality pass rate | Yasir | H | 98% | 20% |  |  |  | Ops SLA Tracker (Avg, Live)
Operations · Data Engineering (Yasir) — Weighted Score
Operations · BI (Ahmad)
6 | Dashboard availability | Ahmad | H | 99.5% | 25% |  |  |  | Ops SLA Tracker (Avg, Live)
7 | Avg report load time (sec) | Ahmad | L | 5 | 15% |  |  |  | Ops SLA Tracker (Avg, Live)
8 | P1 defect resolution (hrs) | Ahmad | L | 8 | 20% |  |  |  | Ops SLA Tracker (Avg, Live)
9 | Active user adoption | Ahmad | H | 70% | 20% |  |  |  | Ops SLA Tracker (Avg, Live)
10 | User CSAT (1-5) | Ahmad | H | 4 | 20% |  |  |  | Ops SLA Tracker (Avg, Live)
Operations · BI (Ahmad) — Weighted Score
PILLAR 2 — DELIVERY (15 new dashboards · pulled from Delivery Tracker + manual)
Delivery · Joint
11 | On-time delivery vs roadmap | Joint | H | 90% | 30% |  |  |  | Delivery Tracker
12 | Avg cycle time (days) | Joint | L | 45 | 20% |  |  |  | Delivery Tracker
13 | Estimation accuracy | Joint | H | 85% | 15% |  |  |  | Manual input — from Azure DevOps
14 | Defect escape rate / dashboard | Joint | L | 2 | 15% |  |  |  | Manual input — from Azure DevOps
15 | UAT first-pass rate | Joint | H | 80% | 20% | 0% | 0% | Red | Delivery Tracker
| Delivery · Joint — Weighted Score | [5 empty] | 0% | Red
Delivery · Data Engineering (Yasir)
16 | Fusion semantic-layer coverage | Yasir | H | 95% | 35% |  |  |  | Manual input — from semantic registry
17 | Pipeline milestone hit rate | Yasir | H | 90% | 35% | 0% | 0% | Red | Delivery Tracker
18 | Pre-prod data quality pass rate | Yasir | H | 95% | 30% |  |  |  | Manual input — from DQ framework
| Delivery · Data Engineering (Yasir) — Weighted Score | [5 empty] | 0% | Red
Delivery · BI (Ahmad)
19 | Visual milestone hit rate | Ahmad | H | 90% | 40% | 0% | 0% | Red | Delivery Tracker
20 | Design review first-pass rate | Ahmad | H | 80% | 30% | 0% | 0% | Red | Delivery Tracker
21 | Stakeholder sign-off cycle (days) | Ahmad | L | 5 | 30% | 9.2222 | 54.22% | Red | Delivery Tracker
| Delivery · BI (Ahmad) — Weighted Score | [5 empty] | 16.27% | Red
OVERALL ROLE SCORE (60% own-role Ops · 30% own-role Delivery · 10% Joint Delivery)
Yasir — overall score
Ahmad — overall score

## Dashboard Portfolio
DASHBOARD PORTFOLIO — Master Register & Stakeholder Governance
Single source of truth for all dashboards. Tier here drives SLA targets in Ops SLA Tracker. Owners, Stakeholders, and Governance Rules captured per dashboard.
ID | Dashboard Name | Domain | Status | Tier | DE Owner | BI Owner | Source System | Refresh Frequency | Refresh Window | Business Sponsor | Data Owner | Change Approver | Escalation Contact | Stakeholder Group | Access Rule | Change Control Rule | Data Sensitivity | Notes
1 | Finance — Daily Cash Position | Finance | Live | P1 | Yasir | Ahmad | Oracle Fusion (Finance) | Daily | Daily by 7 AM AST |  |  |  | CFO + Treasury |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential | Drives daily liquidity decisions
2 | Finance — AR Aging & Collections | Finance | Live | P2 | Yasir | Ahmad | Oracle Fusion (Finance) | Daily | Daily by 8 AM AST |  |  |  | Finance Dept + Collections |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
3 | Finance — AP Status & Payment Run | Finance | Live | P2 | Yasir | Ahmad | Oracle Fusion (Finance) | Daily | Daily by 8 AM AST |  |  |  | Finance Dept + Treasury |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
4 | Finance — Monthly P&L | Finance | Live | P1 | Yasir | Ahmad | Oracle Fusion (Finance) | Monthly | 5th of month by EOD |  |  |  | CFO + Department Heads |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential | Used in monthly close
5 | Finance — Budget vs Actual | Finance | Live | P2 | Yasir | Ahmad | Oracle Fusion (Finance) | Monthly | 5th of month by EOD |  |  |  | Finance Dept + Department Heads |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
6 | Operations — Property Occupancy | Operations | Live | P1 | Yasir | Ahmad | Mixed (Fusion + Manual) | Daily | Daily by 9 AM AST |  |  |  | Operations + Asset Mgmt |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal | Core operational KPI for real estate portfolio
7 | Operations — Lease Renewals & Expiries | Operations | Live | P2 | Yasir | Ahmad | Mixed (Fusion + Manual) | Weekly | Mondays by 9 AM AST |  |  |  | Asset Mgmt + Leasing |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
8 | Operations — Revenue by Asset | Operations | Live | P1 | Yasir | Ahmad | Oracle Fusion (Finance) | Monthly | 5th of month by EOD |  |  |  | Asset Mgmt + CFO |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
9 | Operations — Maintenance Tickets | Operations | Live | P2 | Yasir | Ahmad | Service Desk Tool | Daily | Daily by 7 AM AST |  |  |  | Operations + Facilities |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
10 | HCM — Headcount & Org | HCM | Live | P2 | Yasir | Ahmad | Oracle Fusion (HCM) | Weekly | Mondays by 9 AM AST |  |  |  | HR / People + Department Heads |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
11 | HCM — Attendance & Leave | HCM | Live | P3 | Yasir | Ahmad | Oracle Fusion (HCM) | Weekly | Mondays by 9 AM AST |  |  |  | HR / People |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
12 | HCM — Payroll Summary | HCM | Live | P1 | Yasir | Ahmad | Oracle Fusion (HCM) | Monthly | Payroll cut-off + 1 day |  |  |  | CFO + HR / People |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Restricted | Restricted to senior leadership
13 | Procurement — PO Status & Spend | Procurement | Live | P2 | Yasir | Ahmad | Oracle Fusion (Procurement) | Daily | Daily by 7 AM AST |  |  |  | Procurement Dept |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal | Legacy dashboard — superseded by new Spend Analytics
14 | IT — System Availability | IT SM | Live | P2 | Yasir | Ahmad | Service Desk Tool | Daily | Daily by 7 AM AST |  |  |  | IT Operations |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
15 | Compliance — Regulatory Reporting | Compliance | Live | P1 | Yasir | Ahmad | Mixed (Fusion + Manual) | Monthly | 1st of month by EOD |  |  |  | CSSO + Compliance |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Restricted | Used for NCA / regulatory submissions
16 | Executive — KPI Scorecard | Strategy | Live | P1 | Yasir | Ahmad | Mixed (Fusion + Manual) | Weekly | Mondays by 9 AM AST |  |  |  | C-level + Strategy Dept |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential | Reviewed in weekly leadership meeting
17 | Procurement — Spend Analytics | Procurement | In Build | P1 | Yasir | Ahmad | Oracle Fusion (Procurement) | Daily | Daily by 7 AM AST |  |  |  | Procurement Dept + CFO |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
18 | Procurement — Supplier Performance | Procurement | In Build | P2 | Yasir | Ahmad | Oracle Fusion (Procurement) | Weekly | Mondays by 9 AM AST |  |  |  | Procurement Dept |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
19 | Procurement — PR/PO Cycle Time | Procurement | In Build | P2 | Yasir | Ahmad | Oracle Fusion (Procurement) | Daily | Daily by 7 AM AST |  |  |  | Procurement Dept + Operations |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
20 | Procurement — Contract Compliance | Procurement | In Build | P2 | Yasir | Ahmad | Oracle Fusion (Procurement) | Weekly | Mondays by 9 AM AST |  |  |  | Procurement + Legal |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
21 | Strategy — KPI Scorecard | Strategy | In Scoping | P1 | Yasir | Ahmad | Mixed (Fusion + Manual) | Monthly | 1st of month by EOD |  |  |  | Strategy Dept + C-level |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
22 | Strategy — Initiatives Tracker | Strategy | In Scoping | P2 | Yasir | Ahmad | Azure DevOps | Weekly | Mondays by 9 AM AST |  |  |  | Strategy Dept |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
23 | Strategy — Performance vs Plan | Strategy | In Scoping | P2 | Yasir | Ahmad | Mixed (Fusion + Manual) | Monthly | 5th of month by EOD |  |  |  | Strategy Dept |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
24 | Strategy — TBD #4 | Strategy | In Scoping | P3 | Yasir | Ahmad | TBD | Monthly | TBD |  |  |  | Strategy Dept |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
25 | IT Tickets — SLA & Volume | IT SM | In Build | P2 | Yasir | Ahmad | Service Desk Tool | Daily | Daily by 7 AM AST |  |  |  | IT Operations |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
26 | IT Tickets — Backlog & Aging | IT SM | In Build | P2 | Yasir | Ahmad | Service Desk Tool | Daily | Daily by 7 AM AST |  |  |  | IT Operations |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
27 | HCM — Headcount & Movements | HCM | In Build | P2 | Yasir | Ahmad | Oracle Fusion (HCM) | Weekly | Mondays by 9 AM AST |  |  |  | HR / People + Department Heads |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
28 | HCM — Attrition & Time-to-Hire | HCM | In Build | P2 | Yasir | Ahmad | Oracle Fusion (HCM) | Monthly | 1st of month by EOD |  |  |  | HR / People |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Confidential
29 | TBD A | TBD | Not Started | P3 | Yasir | Ahmad | TBD | TBD | TBD |  |  |  | TBD |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
30 | TBD B | TBD | Not Started | P3 | Yasir | Ahmad | TBD | TBD | TBD |  |  |  | TBD |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal
31 | TBD C | TBD | Not Started | P3 | Yasir | Ahmad | TBD | TBD | TBD |  |  |  | TBD |  | View: Department-wide; Edit: D&A team only | Minor: Approver only. Major: Sponsor + Approver. CR via Azure DevOps. | Internal

## SLA Tiers
SLA TIERS — KPI × Tier Target Matrix
Single source of truth for tier-driven SLA targets. Ops SLA Tracker pulls targets from here based on each dashboard's tier (set in Dashboard Portfolio). Adjust values per organizational requirements.
KPI | P1 | P2 | P3 | Direction | Unit | Notes
Pipeline availability | 99.9% | 99.5% | 99% | H | % | Calendar month, excludes planned maintenance
Data freshness % met | 99% | 95% | 90% | H | % | Window varies per dashboard; set in Portfolio.Refresh Window
Pipeline failures per month | 0 | 2 | 5 | L | Count | Excludes retries that succeed within 30 minutes
Incident MTTR | 2 | 4 | 8 | L | Hours | From incident detection to resolution
Data quality pass rate | 99% | 98% | 95% | H | % | Across all DQ test cases
Dashboard availability | 99.9% | 99.5% | 99% | H | % | Power BI service uptime
Avg report load time | 3 | 5 | 8 | L | Seconds | Top dashboards in tier
P1 defect resolution time | 4 | 8 | 24 | L | Hours | From ticket open to fix deployed
Active user adoption | 80% | 70% | 50% | H | % | Monthly active vs target audience size
User CSAT | 4.3 | 4 | 3.8 | H | Score 1-5 | Quarterly survey average
TIER DEFINITIONS
P1 — Critical | Dashboards used by C-level / regulatory / financial close. Outage triggers immediate escalation.
P2 — Important | Dashboards used by department heads or for operational decisions on a weekly basis. Outage notified within 1 hour.
P3 — Standard | Reference / informational dashboards used periodically. Outage handled within standard SLA, no on-call escalation.

## Ops SLA Tracker
OPS SLA TRACKER — Per-Dashboard Monthly SLA Performance
Targets pull from SLA Tiers based on each dashboard's Tier (set in Dashboard Portfolio). Only Actuals are inputs. RAG auto-calculates. Filter Status = Live to focus on production dashboards.
Reporting Period: | MMM-YYYY
ID | Dashboard Name | Status | Tier | Pipeline Avail. (%) |  |  | Data Freshness (%) |  |  | Pipeline Failures (Cnt) |  |  | MTTR (Hrs) |  |  | DQ Pass Rate (%) |  |  | Dashboard Avail. (%) |  |  | Load Time (Sec) |  |  | P1 Defect Resolution (Hrs) |  |  | Adoption (%) |  |  | CSAT (Scr)
|  |  |  | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG | Target | Actual | RAG
1 | Finance — Daily Cash Position | Live | P1 | 99.9% |  |  | 99% |  |  | 0 |  |  | 2 |  |  | 99% |  |  | 99.9% |  |  | 3 |  |  | 4 |  |  | 80% |  |  | 4.3
2 | Finance — AR Aging & Collections | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
3 | Finance — AP Status & Payment Run | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
4 | Finance — Monthly P&L | Live | P1 | 99.9% |  |  | 99% |  |  | 0 |  |  | 2 |  |  | 99% |  |  | 99.9% |  |  | 3 |  |  | 4 |  |  | 80% |  |  | 4.3
5 | Finance — Budget vs Actual | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
6 | Operations — Property Occupancy | Live | P1 | 99.9% |  |  | 99% |  |  | 0 |  |  | 2 |  |  | 99% |  |  | 99.9% |  |  | 3 |  |  | 4 |  |  | 80% |  |  | 4.3
7 | Operations — Lease Renewals & Expiries | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
8 | Operations — Revenue by Asset | Live | P1 | 99.9% |  |  | 99% |  |  | 0 |  |  | 2 |  |  | 99% |  |  | 99.9% |  |  | 3 |  |  | 4 |  |  | 80% |  |  | 4.3
9 | Operations — Maintenance Tickets | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
10 | HCM — Headcount & Org | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
11 | HCM — Attendance & Leave | Live | P3 | 99% |  |  | 90% |  |  | 5 |  |  | 8 |  |  | 95% |  |  | 99% |  |  | 8 |  |  | 24 |  |  | 50% |  |  | 3.8
12 | HCM — Payroll Summary | Live | P1 | 99.9% |  |  | 99% |  |  | 0 |  |  | 2 |  |  | 99% |  |  | 99.9% |  |  | 3 |  |  | 4 |  |  | 80% |  |  | 4.3
13 | Procurement — PO Status & Spend | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
14 | IT — System Availability | Live | P2 | 99.5% |  |  | 95% |  |  | 2 |  |  | 4 |  |  | 98% |  |  | 99.5% |  |  | 5 |  |  | 8 |  |  | 70% |  |  | 4
15 | Compliance — Regulatory Reporting | Live | P1 | 99.9% |  |  | 99% |  |  | 0 |  |  | 2 |  |  | 99% |  |  | 99.9% |  |  | 3 |  |  | 4 |  |  | 80% |  |  | 4.3
16 | Executive — KPI Scorecard | Live | P1 | 99.9% |  |  | 99% |  |  | 0 |  |  | 2 |  |  | 99% |  |  | 99.9% |  |  | 3 |  |  | 4 |  |  | 80% |  |  | 4.3
17 | Procurement — Spend Analytics | In Build | P1
18 | Procurement — Supplier Performance | In Build | P2
19 | Procurement — PR/PO Cycle Time | In Build | P2
20 | Procurement — Contract Compliance | In Build | P2
21 | Strategy — KPI Scorecard | In Scoping | P1
22 | Strategy — Initiatives Tracker | In Scoping | P2
23 | Strategy — Performance vs Plan | In Scoping | P2
24 | Strategy — TBD #4 | In Scoping | P3
25 | IT Tickets — SLA & Volume | In Build | P2
26 | IT Tickets — Backlog & Aging | In Build | P2
27 | HCM — Headcount & Movements | In Build | P2
28 | HCM — Attrition & Time-to-Hire | In Build | P2
29 | TBD A | Not Started | P3
30 | TBD B | Not Started | P3
31 | TBD C | Not Started | P3

## Delivery Tracker
DELIVERY TRACKER — 15 New Dashboards
7 stages: BRD → Design Approval → Data Model → Pipeline → Visual → UAT → Production. Yellow = inputs; Status, % Complete, and Summary KPIs auto-calculate. Summary feeds Scorecard.
| Dashboard | Domain | S1: BRD |  | S2: Design Approval |  | S3: Data Model (Fusion) |  | S4: Pipeline (DE) |  | S5: Visual (BI) |  | S6: UAT |  | S7: Production |  | Status | % Complete
|  |  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | Procurement — Spend Analytics | Procurement | 2026-01-15 | 2026-01-20 | 2026-02-01 | 2026-02-05 | 2026-02-20 | 2026-02-25 | 2026-03-15 | 2026-03-20 | 2026-04-05 | 2026-04-10 | 2026-04-25 | 2026-05-01 | 2026-05-15 |  | UAT Complete | 85.71%
2 | Procurement — Supplier Performance | Procurement | 2026-01-30 | 2026-02-03 | 2026-02-15 | 2026-02-20 | 2026-03-05 | 2026-03-10 | 2026-03-25 | 2026-04-02 | 2026-04-20 | 2026-05-05 | 2026-05-15 |  | 2026-06-01 |  | Visual Complete | 71.43%
3 | Procurement — PR/PO Cycle Time | Procurement | 2026-02-01 | 2026-02-05 | 2026-02-20 | 2026-02-28 | 2026-03-15 | 2026-03-20 | 2026-04-10 | 2026-05-03 | 2026-04-30 |  | 2026-05-20 |  | 2026-06-05 |  | Pipeline Complete | 57.14%
4 | Procurement — Contract Compliance | Procurement | 2026-02-15 | 2026-02-20 | 2026-03-05 | 2026-03-12 | 2026-04-01 | 2026-04-25 | 2026-04-25 |  | 2026-05-15 |  | 2026-06-05 |  | 2026-06-20 |  | Data Model Complete | 42.86%
5 | Strategy — KPI Scorecard | Strategy | 2026-02-25 | 2026-03-01 | 2026-03-20 | 2026-04-05 | 2026-04-10 |  | 2026-05-01 |  | 2026-05-20 |  | 2026-06-10 |  | 2026-06-25 |  | Design Approved | 28.57%
6 | Strategy — Initiatives Tracker | Strategy | 2026-03-01 | 2026-03-10 | 2026-04-01 | 2026-04-15 | 2026-04-25 |  | 2026-05-15 |  | 2026-06-05 |  | 2026-06-20 |  | 2026-07-05 |  | Design Approved | 28.57%
7 | Strategy — Performance vs Plan | Strategy | 2026-03-15 | 2026-04-20 | 2026-04-05 |  | 2026-04-25 |  | 2026-05-20 |  | 2026-06-10 |  | 2026-06-30 |  | 2026-07-15 |  | BRD Complete | 14.29%
8 | Strategy — TBD #4 | Strategy | [14 empty] | Not Started | 0%
9 | IT Tickets — SLA & Volume | IT SM | 2026-02-10 | 2026-02-15 | 2026-03-01 | 2026-03-08 | 2026-03-25 | 2026-04-02 | 2026-04-20 | 2026-05-05 | 2026-05-10 |  | 2026-05-30 |  | 2026-06-15 |  | Pipeline Complete | 57.14%
10 | IT Tickets — Backlog & Aging | IT SM | 2026-02-20 | 2026-02-25 | 2026-03-10 | 2026-03-18 | 2026-04-01 | 2026-04-08 | 2026-04-25 | 2026-04-30 | 2026-05-15 |  | 2026-06-01 |  | 2026-06-15 |  | Pipeline Complete | 57.14%
11 | HCM — Headcount & Movements | HCM | 2026-03-05 | 2026-03-12 | 2026-03-25 | 2026-04-08 | 2026-04-20 |  | 2026-05-10 |  | 2026-05-30 |  | 2026-06-20 |  | 2026-07-05 |  | Design Approved | 28.57%
12 | HCM — Attrition & Time-to-Hire | HCM | 2026-03-10 | 2026-03-20 | 2026-04-01 |  | 2026-04-25 |  | 2026-05-15 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-10 |  | BRD Complete | 14.29%
13 | TBD A | TBD | [14 empty] | Not Started | 0%
14 | TBD B | TBD | [14 empty] | Not Started | 0%
15 | TBD C | TBD | [14 empty] | Not Started | 0%
Portfolio average | [17 empty] | 32.38%
DELIVERY KPI SUMMARY (computed from above — feeds Scorecard)
# | Delivery KPI | [16 empty] | Value
1 | Portfolio % complete (avg) | [16 empty] | 32.38%
2 | On-time delivery vs roadmap (production)
3 | Avg cycle time — BRD to Production (days)
4 | BRD on-time rate | [16 empty] | 0%
5 | Design Approval first-pass rate (on-time) | [16 empty] | 0%
6 | Stakeholder sign-off cycle (Design Approval, days) | [16 empty] | 9.2222
7 | Pipeline milestone hit rate (Yasir) | [16 empty] | 0%
8 | Visual milestone hit rate (Ahmad) | [16 empty] | 0%
9 | UAT first-pass rate | [16 empty] | 0%
LEGEND | bar: 2026-02-20 to 2026-03-18
| Yellow cells | Input cells — milestone dates
| Light red cell | Actual date later than planned
| Green % Complete | Delivered (100%)
| Amber % Complete | In flight (50–99%)
| Red % Complete | Below 50%

## Lookups
LOOKUPS — Dropdown Source Lists
All dropdowns in the workbook reference the columns below. To add an option, append it to the relevant column.
Tiers | Statuses | Owners | Domains | Frequency | Source Systems | Data Sensitivity | RAG
P1 | Live | Yasir | Finance | Real-time | Oracle Fusion (Finance) | Public | Green
P2 | In Build | Ahmad | Procurement | Hourly | Oracle Fusion (Procurement) | Internal | Amber
P3 | In Scoping | Joint | HCM | Daily | Oracle Fusion (HCM) | Confidential | Red
| Not Started |  | IT SM | Weekly | Service Desk Tool | Restricted
| Retired |  | Strategy | Monthly | Azure DevOps
|  |  | Operations | Quarterly | Mixed (Fusion + Manual)
|  |  | Compliance |  | Manual / Excel
|  |  | TBD |  | TBD